## Sheet1
Devided work that needs to be done | Amount of time need to put in | Finished before | Planned working days
Literature search | 2 days | 2023-12-22 | 20 and 21 december
Design ASR system | 1 day | 2023-01-09 | 2023-01-08
Producing schedule for injection, extraction and storage | 1 day | 2023-01-10 | 2023-01-09
Reduce waste of injected drinking water | 1 day | 2023-01-15 | 2023-01-11
Apply guidelines for injection pressure and maximum velocity | 1 day | 2023-01-18 | 2023-01-15
Run model for 10 years with a start-up year and less extracted volume | 1 day | 2023-01-22 | 2023-01-18
Making conclusion and finish report | 1 day | 2023-01-24 | 2023-01-22